FIELD TICKET & COST MANAGEMENT

In Oil & Gas Operations

A Practical Guide for Drilling Companies and Oil & Gas Operators

How costs are captured, recorded, approved, and paid — and where the process breaks down.

Prepared by Enter My Invoice (EMI)

entermyinvoice.com

Introduction

Drilling a well is one of the most capital-intensive activities in the oil and gas industry. A single well can cost anywhere from $1 million to over $15 million depending on depth, complexity, and location. Every dollar spent — from the drilling contractor's day rate to the mud engineer's chemical additions — must be captured in the field, approved by the right people, and reconciled against a pre-approved budget called an Authority for Expenditure (AFE).

The challenge is that this cost data comes from dozens of different sources, on different forms, at different times, submitted through different systems. The result is a process that is slow, error-prone, and expensive to manage — on both the operator and contractor side.

This document explains how the field ticket and cost management process works in practice — from the rig floor to the operator's accounts payable system — and identifies where the greatest inefficiencies and opportunities for improvement exist.

Part 1: The Key People in the Cost Process

Before understanding how costs flow, it helps to understand who is responsible for them. On any drilling operation, there are typically two overlapping chains of command — one on the operator side and one on the drilling contractor side — and they intersect at the rig.

| Role | Responsibility in the Cost Process |
| --- | --- |
| Operator — Company Man / Drilling Superintendent | The operator's representative on the rig. They approve or dispute every cost incurred at the wellsite. They are responsible for tracking actual spend against the AFE and escalating overruns. |
| Operator — Drilling Engineer | Designs the well program and sets the AFE budget. Reviews daily cost summaries. Authorizes significant cost deviations or scope changes. |
| Operator — AFE Owner / Finance | Holds the budget authority for the well. Signs off on the original AFE and any supplements. Receives the reconciled cost data for payment processing after the well is complete. |
| Drilling Contractor — Toolpush | The drilling contractor's senior representative on site. Responsible for completing the Daily Drilling Report (DDR), capturing all rig-related costs, and submitting day rate invoices. |
| Drilling Contractor — Driller | Operates the rig on a shift basis. Tracks rig status codes — drilling, tripping, waiting, non-productive time — which directly determine what rate the contractor charges. |
| Third-Party Service Companies | Each outside service has their own field representative who generates a ticket for their work. These are submitted separately and approved by the company man independently. |
| Back-Office / AP (Both Sides) | On the operator side, AP processes approved invoices. On the contractor side, back-office staff submit invoices and track receivables. Both carry the burden of manual reconciliation. |

Part 2: The AFE — The Budget That Controls Everything

The Authority for Expenditure (AFE) is the financial blueprint for a well. Before a single bit hits the ground, the operator prepares an AFE that estimates every cost associated with drilling, completing, and equipping the well.

### What an AFE Contains

| AFE Line Item | What It Covers |
| --- | --- |
| Drilling Contractor | Day rate estimate based on projected days to drill, plus standby, moving, and rig-up/rig-down days |
| Directional Drilling | MWD/LWD tool rentals, steering fees, data services |
| Drilling Fluids / Mud | Fluid system design, daily mud engineer charges, chemical additions |
| Cementing | Casing cement jobs — surface, intermediate, and production casing |
| Bits | Estimated number and type of bits based on the well program |
| Casing & Tubulars | Purchase cost of surface, intermediate, and production casing strings |
| Wellsite Services | Wireline, perforating, formation evaluation, testing |
| Location & Civil | Road construction, lease preparation, rig pad, environmental controls |
| Fuel | Diesel for rig, light plants, accommodations, service vehicles |
| Rentals | Drill collars, jars, BHA tools, BOP equipment |
| Accommodations & Catering | Camp or hotel costs for rig crew and service personnel |
| Contingency | Typically 10-15% of total AFE to cover unexpected costs |

| KEY POINT | The AFE is not just a budget — it is an authorization. Costs outside the AFE require a supplement that must go back through the full approval chain. This is why real-time cost tracking is so critical. |
| --- | --- |

### AFE Tracking During the Well

Every day the well is drilling, the company man is manually tracking actual costs against each AFE line — typically in a spreadsheet updated from handwritten or emailed field data. The result is a 12-24 hour lag between costs incurred and costs reflected in the AFE tracking system.

The drilling engineer back in the office often has no real-time visibility into well costs. By the time a significant overrun is identified, it may already be too late to course-correct.

Part 3: How Drilling Contractor Costs Are Captured

The drilling contractor operates on a day rate model. The Daily Drilling Report (DDR) is the document that drives everything — it captures what the rig was doing every hour and determines what the contractor bills.

### The Daily Drilling Report (DDR)

The DDR is completed by the toolpush at the end of each 24-hour reporting period. It captures:

- Footage drilled and current measured depth

- Rig status for every hour — drilling, tripping, waiting on cement, NPT, standby

- Equipment operated and consumables used

- Personnel on location

- Third-party services called in and their estimated costs

- Any notable events — stuck pipe, weather delay, HSE incidents

| IMPORTANT | The rig status codes on the DDR determine what rate the contractor bills. Every hour of status code is a billing decision. |
| --- | --- |

### How the Day Rate Invoice Is Generated

| # | Stage | What It Means for You |
| --- | --- | --- |
| 1 | DDR Completed | Toolpush fills out the DDR on paper, in Excel, or in a system like WellView or Pason |
| 2 | Status Coded | Each hour is assigned a rig status code that maps to a contracted billing rate |
| 3 | Sent to Back Office | DDR is emailed or uploaded — back-office receives it often the next morning |
| 4 | Invoice Created | Someone manually keys the DDR data into the invoicing system and generates a daily invoice |
| 5 | Submitted to Portal | Invoice is uploaded to the operator portal — OpenInvoice, SAP Ariba, Jobutrax, etc. |
| 6 | Operator Reviews | Company man or drilling engineer logs in to review and approve |
| 7 | AP Processes Payment | Approved invoice flows to accounts payable — typically net 30-60 days |

### Common Causes of Day Rate Disputes

| Dispute Type | Why It Happens |
| --- | --- |
| Status Code Disagreement | Company man and toolpush disagree on whether downtime was contractor-caused (breakdown rate) or operator-caused (standby rate) |
| NPT Classification | Who absorbs non-productive time determines the difference between zero and full day rate billing |
| Shift Change Timing | Ambiguous shift boundaries create hours that appear in two DDRs simultaneously |
| Third-Party Charges | Confusion over whether outside services appear on the rig invoice or are billed directly |
| Standby vs. Breakdown | Equipment issues in the grey zone between maintenance and unplanned breakdown |

Part 4: How Outside Service & Product Costs Are Captured

Beyond the drilling contractor's day rate, a well involves dozens of third-party services and product deliveries — each generating their own field ticket, submitted independently. This is where cost management becomes exponentially more complex.

### The Field Ticket

Every third-party service or product delivery is documented on a field ticket. It identifies the service or product, specifies quantity and pricing, references the AFE and PO, and is signed by the company man as field-level authorization. Without that signature, the service company cannot invoice.

A lost or unsigned field ticket means delayed payment. A disputed ticket means months of chasing — for work that was performed and accepted at the rig.

### Major Outside Cost Categories on a Typical Well

| Service / Product | How It Is Billed |
| --- | --- |
| Directional Drilling | MWD/LWD tool rental (daily rate), survey data, directional driller on site, steering software. A complex horizontal well may accumulate $200K-$500K in directional charges. |
| Drilling Fluids / Mud | Daily mud engineer, chemical additions priced per unit (barite, bentonite, polymer systems), waste fluid disposal. |
| Cementing | Each casing string generates a separate ticket: bulk cement, additives, pump truck time, mixing equipment. A three-string well generates three cement tickets. |
| Wireline / Logging | Charged per run or per day. Open-hole logging, perforating, completion tools. Each run is a separate job ticket. |
| Drill Bits | Each bit tracked individually. Charged per bit or on a footage basis. Typically 3-8 bits per well. |
| Rental Tools | Drill collars, jars, reamers, BOP equipment — all rented daily. Multiple rental companies may be on one well simultaneously. |
| Fuel Delivery | Bulk diesel delivered to location generates a delivery ticket. Remote locations may see multiple deliveries per week. |
| Water Hauling | Fresh water for mud mixing delivered by tanker. Each load generates a signed ticket. |
| Waste Disposal | Cuttings haul-off, produced water disposal. Each truck load requires a ticket cross-referenced to a disposal manifest. |
| Casing & Tubulars | Often operator-purchased but delivered to location. Material delivery tickets must be matched to a purchase order. |
| Accommodations / Catering | Daily charges per head. Camp operator submits monthly with daily headcount records. |
| Environmental / Reclamation | Spill response, containment, environmental monitoring — billed on time-and-materials basis. |

| REALITY CHECK | It is not uncommon for a company man to be managing cost data from 8-12 different service companies simultaneously, each with their own ticket format and pricing structure. The daily cost compilation takes 45-90 minutes — time that could be spent supervising the actual drilling operation. |
| --- | --- |

Part 5: The Approval and Payment Chain

Once field tickets are generated, the journey from wellsite approval to payment can take 30 to 90 days — or longer when disputes occur. This timeline is the primary driver of cash flow challenges across the oilfield services sector.

### The Three-Way Match

Before an invoice is approved for payment, most operators require a three-way match between the Purchase Order, the Field Ticket, and the Invoice. When all three align, payment proceeds. When they do not — which is common — the invoice enters a dispute queue that can take weeks to resolve.

### Typical Payment Timeline

| Timeline | What Happens |
| --- | --- |
| Day 0 | Service performed. Field ticket generated and signed by company man. |
| Day 1-5 | Field ticket transmitted to operator office. Reviewed by drilling engineer. |
| Day 5-15 | Service company converts field ticket to invoice. Submits through operator portal. |
| Day 10-25 | Operator AP performs three-way match. |
| Day 20-40 | Invoice approved for payment if no disputes. Batched for processing. |
| Day 30-60 | Payment issued. Net 30 or net 45 terms most common in western Canada. |
| Day 60-90+ | Payment received if disputes caused delays. Interest may accrue. |

| THE CASHFLOW IMPACT | A service company running 5 rigs generating $500K/month in billings with an average DSO of 55 days has over $900,000 in outstanding receivables at any given time — nearly two months of revenue financing the operator's operations at the service company's cost of capital. |
| --- | --- |

Part 6: Where the Process Breaks Down

The current field ticket and cost management process was designed for a simpler era. Today's wells are more complex, the service ecosystem is larger, and transaction volumes are higher — but the underlying process has not fundamentally changed in decades.

| Pain Point | What It Costs the Business |
| --- | --- |
| Manual Data Entry — Double and Triple Keying | The same cost data is typically entered by hand three to four times. Each entry is a new opportunity for error. |
| Paper Tickets Lost or Damaged | Lost tickets mean delayed or disputed invoices — and service companies chasing signatures for work performed weeks ago. |
| No Real-Time AFE Visibility | AFE overruns are discovered after the fact — when it is too late to course-correct or avoid a supplementary approval. |
| Portal Complexity for Small Companies | A service company working with five operators may submit invoices through five different portals. Small companies often lack the administrative capacity to manage this. |
| Status Code Disputes Create Invoice Pileup | A single disputed day rate invoice can hold up approval of subsequent invoices — creating a cascading payment delay across the entire well. |
| Reconciliation at Well Completion | End-of-well reconciliation requires manually matching dozens of invoices, field tickets, POs, and delivery receipts accumulated over 30-90 days of drilling. |
| Third-Party Pricing Not Pre-Loaded | When pricing is not in the operator's system, every invoice line must be manually checked against the contract — the single biggest source of processing delay. |

Part 7: The Automation Opportunity

The oil and gas industry has invested heavily in automating the physical side of drilling — automated pipe handling, real-time formation evaluation, AI-assisted directional drilling. But the administrative and financial side of a drilling operation remains largely manual. This gap represents one of the most significant and underserved efficiency opportunities in the oilfield services sector.

### What a Fully Automated Cost Management Workflow Looks Like

| # | Stage | What It Means for You |
| --- | --- | --- |
| 1 | Digital Field Capture | The toolpush completes the DDR digitally. Service reps submit field tickets through a mobile app. Delivery tickets are photographed and OCR-processed. Nothing is hand-keyed. |
| 2 | Automatic AFE Coding | Each captured cost is automatically assigned to the correct AFE line item. The system flags anything it cannot auto-code for human review. |
| 3 | Real-Time AFE Dashboard | The company man, drilling engineer, and AFE owner all see a live view of actual vs. budgeted costs. Variance alerts fire automatically. |
| 4 | Automated Routing | Field tickets route digitally to the company man for field approval, then to the drilling engineer, then to the AFE owner for out-of-scope items. |
| 5 | Invoice Generation | Approved field tickets are automatically converted into properly formatted invoices. No back-office re-keying. No portal manual entry. |
| 6 | Portal Submission | The invoice is automatically submitted to the operator's portal — OpenInvoice, SAP Ariba, Jobutrax — with all required fields pre-populated. |
| 7 | Three-Way Match | PO, field ticket, and invoice are matched automatically. Exceptions are flagged. Clean matches proceed to payment without human intervention. |
| 8 | Payment & Reconciliation | Payment issues on contracted terms. AFE updates automatically. A fully reconciled well cost report is ready at TD — no manual compilation required. |

### The Measurable Business Impact

| Benefit | Business Impact |
| --- | --- |
| Reduced DSO for Service Companies | Same-day invoice submission compresses the payment cycle by 2-3 weeks. On $500K/month in billings, that frees $250K-$375K of working capital. |
| Fewer Disputes | Digitally signed, timestamped field tickets eliminate the most common causes of invoice disputes. |
| Real-Time AFE Control for Operators | Operators can course-correct mid-well. Costly supplementary AFE approvals are avoided in many cases. |
| Back-Office Efficiency | A drilling contractor running 10 rigs generates 300+ invoices per month. Automation eliminates the equivalent of 1-2 full-time administrative positions. |
| Faster Well Reconciliation | A complete, reconciled well cost report at the push of a button — instead of a week-long manual exercise. |
| Data for Benchmarking | Operators gain structured, comparable cost data across wells and contractors — enabling better AFE budgeting and contractor performance scoring. |

The oil and gas industry drilled over 24,000 wells across western Canada between 2020 and 2024. Each generated hundreds of field tickets, daily reports, and invoices — the vast majority managed through manual processes. The opportunity to recover that cost through automation is enormous.

Part 8: How Faster Data Helps Drilling Companies Win More Business

Most drilling contractors think about invoice automation as a back-office efficiency tool. That framing undersells it. When a drilling company can deliver real-time cost data, clean field tickets, and same-day invoice submission to an operator, it is not just reducing its own administrative burden — it is removing friction from the operator's most important daily workflow. That becomes a competitive advantage that wins contracts.

In a western Canadian market running 5,500+ wells per year with disciplined operator capital spending, contracts are no longer awarded purely on day rate. Operators choose contractors who make their lives easier — operationally and administratively. The drilling company that can demonstrate transparent, automated cost data delivery is having a fundamentally different conversation with operators than its competitors.

### 1.  You Become the Easiest Contractor to Work With

Operators have a finite number of drilling engineers and company men. Their administrative burden is real — AFE tracking, invoice approvals, cost reconciliation, portal management. A drilling contractor that automates and accelerates that workflow is actively reducing the operator's workload. When two contractors are at similar day rates, the one who removes administrative friction wins.

The Pitch: "Our field tickets are digital, submitted same-day, pre-coded to your AFE lines, and hit your OpenInvoice portal automatically. Your team does not chase our paperwork."

### 2.  Faster Data Helps Operators Make Better Decisions Mid-Well

When cost data flows to the operator in real time rather than with a 24-hour lag, the drilling engineer can act faster on cost trends, NPT events, and scope decisions. A drilling contractor who enables that visibility is not just a vendor — they are a partner in well delivery. That relationship earns longer-term, larger-volume contracts.

| Benefit to Operator | Why It Matters for Contract Renewal |
| --- | --- |
| Real-Time AFE Tracking | Operator can see a cost category trending over budget and authorize a scope change before it becomes a supplementary AFE — saving management time and protecting the well program |
| NPT Visibility | Downtime events are visible as they happen, not 24 hours later. Operator can mobilize a solution faster, reducing the total NPT duration and its cost impact |
| Performance vs. Offset Wells | Live cost-per-metre and spud-to-release data lets the operator compare this well's performance against offsets in real time — and confirms they chose the right contractor |
| Scope Decision Support | When the operator is deciding whether to run an additional casing string or push to TD, having accurate real-time cost data against AFE makes the decision faster and better informed |

### 3.  It Signals Operational Sophistication

The technology a drilling company uses to manage its administrative process signals something about how it manages everything else. Operators make assumptions — a contractor still running paper DDRs is probably also slower to respond to downtime events, slower to surface problems, and slower to mobilize solutions. A contractor with a digital field ticket and real-time cost submission system signals that they run a tight operation across the board.

| IN THE BID ROOM | Walking into a bid presentation and showing a live dashboard of real-time well cost data — with AFE tracking by line item, by day, and by well phase — is a visual that very few drilling contractors in western Canada can currently match. |
| --- | --- |

### 4.  Clean Data Protects Your Day Rate in Disputes

The most common reason drilling invoices are disputed is ambiguity around rig status codes. Was that four hours waiting on cement at full day rate or standby rate? When your field tickets are digitally timestamped, status-coded at the time of the event, and signed off by the company man in real time, there is nothing to dispute. The data is clean, contemporaneous, and on the record.

For a drilling company running 10 rigs at $25,000/day, even a 5% reduction in disputed hours recovers hundreds of thousands of dollars annually. That is not a rounding error — it is the equivalent of a full rig-month of revenue.

### 5.  Better Financials Improve Your Bid Position

Drilling contracts — especially multi-well programs — are sometimes awarded partly on financial strength. An operator committing to a 10-well program wants confidence the contractor can fund their operations without cash flow problems causing crew or equipment disruptions mid-program. A drilling company with compressed DSO has better working capital, less debt on its revolver, and stronger financial ratios. That makes them a lower-risk contractor in the operator's eyes.

### 6.  Historical Data Builds a Better Bid Every Time

When your cost data is captured digitally and flows cleanly through every well, you accumulate something most drilling contractors do not have — accurate, structured historical performance data. That data makes your next bid materially stronger.

| Performance Metric | Why Operators Care About It |
| --- | --- |
| Actual Cost Per Metre | Show operators your real cost-per-metre on comparable offset wells — not an estimate. This is the number operators use to validate AFE budgets. |
| Historical NPT Rate | Your NPT percentage by formation, by rig, and by season — benchmarked against industry averages. Operators pay a premium for contractors with demonstrably lower NPT. |
| Spud-to-Release Times | Your average well duration on similar profiles — the number that most directly drives the operator's AFE accuracy for future wells in that area. |
| Day Rate Recovery Rate | Your invoiced day rate versus your collected rate after disputes — a metric that demonstrates billing discipline and financial predictability to operators. |

### The Assembled Pitch — Three Levels Simultaneously

When a drilling company walks into an operator meeting with real-time cost data capability, the conversation operates on three levels at once:

Operational: "Our digital field tickets give your team real-time AFE tracking by line item, by day, and by well phase. No more 7am calls asking where you are against budget."

Financial: "Our same-day invoice submission means your AP team processes clean, pre-coded invoices — not chasing field tickets from three weeks ago. Your DSO on our wells will be materially lower than on your other programs."

Strategic: "We have the performance data from our last 40 wells in this basin — cost per metre, NPT rate, spud-to-release. Let us show you what your cost exposure and schedule risk look like with us versus the market average."

That is not a day rate conversation. That is a partnership conversation. And it is one that very few drilling contractors in western Canada are currently capable of having — which is exactly why it wins.

### What This Requires

Delivering on this pitch requires a single foundational capability: digital, real-time field ticket capture that flows automatically into invoice submission and AFE tracking. That is exactly what EMI provides. The drilling company's investment is minimal. The competitive return — in contracts won, disputes avoided, and DSO compressed — is significant.

| 01 Digital DDR & Field Tickets Eliminate paper. Capture costs at the moment they occur, with timestamps and digital sign-off. | 02 Same-Day Invoice Submission Field ticket approved → invoice generated → portal submitted, all without back-office re-keying. | 03 Real-Time AFE Dashboard Operator sees live actual vs. budget by line item. You become the most transparent contractor on their roster. |
| --- | --- | --- |
| 04 Dispute-Proof Audit Trail Every status code, every ticket, every approval — timestamped and signed. No grey areas. No payment delays. | 05 Historical Performance Data Structured well data that builds a stronger bid every time you walk into an operator's office. | 06 Compressed DSO Faster submission, fewer disputes, faster approval. Cash in the bank faster — with better financial ratios to show for it. |

About Enter My Invoice (EMI)

Enter My Invoice (EMI) is a Canadian technology company focused on reducing the administrative burden of invoice submission for oilfield service companies. EMI's platform automates the entry, formatting, and submission of invoices into operator portals — eliminating manual keying, reducing errors, and compressing the time from field ticket to payment.

EMI works with drilling contractors, directional drilling companies, mud companies, cementing contractors, rental tool providers, and a wide range of oilfield services businesses operating in Alberta, British Columbia, Saskatchewan, and beyond.

If your business is managing field tickets and invoices manually — or if you are an operator looking for a better way to track well costs against AFE in real time — we would welcome the opportunity to show you what is possible.

Enter My Invoice (EMI)

entermyinvoice.com

Faster tickets. Cleaner invoices. Faster payment.